## WBS
QuantAgent Improvement Work Breakdown Structure
Editable 12-week planning baseline. Start date, roles, status, priority, and risk are planning defaults; update blue-text inputs as team capacity and release dates are confirmed.
WBS ID | Workstream | Task / Deliverable | Owner Role | Predecessor | Start | Finish | Duration (days) | Effort (days) | % Complete | Status | Priority | Risk | Acceptance Check | Evidence / Source | Notes
1.0 | Program control | Kickoff, scope lock, delivery cadence, and evidence register | Product / Delivery |  | 2026-08-17 | 2026-08-18 | 2 | 3 | 100% | Not Started | P0 | Medium | Roles assigned; weekly cadence and acceptance evidence register published | README.md; docs/PROJECT_FLOW_AND_DEBT_GUIDE.md | Planning baseline
1.1 | Program control | Create reproducible fixture + real-data validation matrix | QA / Quant Research | 1.0 | 2026-08-18 | 2026-08-21 | 4 | 4 | 100% | Not Started | P0 | High | Matrix covers fixture, integration, and DSN-gated real-data checks | README.md local deterministic profile; 진행상황-개선기획.md §7 | Real-data checks remain DSN-gated
2.0 | Truthful presentation | Remove unsupported FE walk-forward claim and related copy (P-4) | Frontend Engineer | 1.0 | 2026-08-20 | 2026-08-20 | 1 | 1 | 0% | Not Started | P0 | Low | No walk-forward claim remains where no rolling validation is implemented | 진행상황-개선기획.md §5 P-4 | Fast, low-risk correction
2.1 | Truthful presentation | Add FE regression coverage for updated performance copy | Frontend Engineer | 2.0 | 2026-08-21 | 2026-08-21 | 1 | 1 | 0% | Not Started | P1 | Low | Targeted FE test proves removed claim cannot regress | FE scripts; 진행상황-개선기획.md §5
3.0 | Point-in-time data | Implement point-in-time liquid-universe query using prior 90-day trading value (P-1) | Data / Backend Engineer | 1.0 | 2026-08-22 | 2026-08-25 | 4 | 5 | 100% | Not Started | P0 | High | Universe is computed as-of backtest start; no current-market-cap selection | 진행상황-개선기획.md §7 P-1; ai/ai_graph/data_sources/db.py | Use editable DSN only in authorized environment
3.1 | Point-in-time data | Unit and integration tests for as-of universe and minimum history | QA / Data Engineer | 3.0 | 2026-08-25 | 2026-08-27 | 3 | 4 | 100% | Not Started | P0 | High | Tests cover 90-day window, ≥30 observations, and ranking determinism | 진행상황-개선기획.md §7 P-1
3.2 | Point-in-time data | Reproduce candidate-ranking change on real data and capture evidence | Quant Research | 3.1 | 2026-08-28 | 2026-08-31 | 4 | 5 | 100% | Not Started | P0 | High | DSN-enabled harness records survivor vs point-in-time candidate ranking comparison | 진행상황-개선기획.md §7 real-data reproduction | Blocked until authorized DSN is available
4.0 | Out-of-sample reporting | Expose holdout-only headline metrics, candidate count, and deflated Sharpe (P-3) | AI / Backend Engineer | 3.1 | 2026-08-29 | 2026-09-02 | 5 | 6 | 100% | Not Started | P0 | High | Headline uses untouched holdout; report displays candidate N and DSR with provenance | 진행상황-개선기획.md §2 P-3; §5 | No hard DSR gate
4.1 | Out-of-sample reporting | Update report/FE projections and API contract tests for transparent metrics | Frontend + QA | 4.0 | 2026-09-02 | 2026-09-04 | 3 | 4 | 100% | Not Started | P0 | Medium | API and UI contract tests prove metric labels and values agree | README MVP spine; ai/tests/contracts; fe scripts
5.0 | Recommendation safety | Implement three-fold consistency abstention gate (P-2) | AI / Quant Engineer | 4.0 | 2026-09-03 | 2026-09-08 | 6 | 7 | 100% | Not Started | P0 | High | Recommendation withheld unless 3/3 positive folds and mean Sharpe ≥ 0.5 | 진행상황-개선기획.md §7 P-2 | Must distinguish abstention from failure
5.1 | Recommendation safety | Test abstention states, reason codes, and 'no recommendation' UX | QA + Frontend | 5.0 | 2026-09-08 | 2026-09-10 | 3 | 4 | 100% | Not Started | P0 | Medium | UI clearly renders cash/no-recommendation state and API reason | 진행상황-개선기획.md §5 P-2
5.2 | Recommendation safety | Measure gate trigger rate and return-dispersion effect on real data | Quant Research | 5.1 | 2026-09-11 | 2026-09-13 | 3 | 4 | 100% | Not Started | P1 | High | Evidence records trigger rate near planning target and compares dispersion | 진행상황-개선기획.md §5 P-2; §7 | DSN-gated
6.0 | Backtest correctness | Add indicator warm-up/min-period enforcement (P-5) | AI / Quant Engineer | 1.1 | 2026-09-04 | 2026-09-06 | 3 | 4 | 100% | Not Started | P1 | Medium | Indicators are NaN/unavailable before their required lookback | 진행상황-개선기획.md §2 P-5
6.1 | Backtest correctness | Add regression tests for insufficient history and early-window signals | QA / Quant Engineer | 6.0 | 2026-09-07 | 2026-09-08 | 2 | 3 | 100% | Not Started | P1 | Medium | Tests reject/withhold early-window signals for all relevant lookbacks | 진행상황-문제정의-2.md A-2; 진행상황-개선기획.md §5
7.0 | Release assurance | Run targeted unit, contract, integration, and fixture smoke suite | QA Engineer | 2.1,4.1,5.1,6.1 | 2026-09-14 | 2026-09-17 | 4 | 5 | 100% | Not Started | P0 | High | All targeted checks pass; failures are triaged with owner and evidence | README verification contract; project tests
7.1 | Release assurance | Run authorized real-data validation and document limits | QA + Quant Research | 3.2,5.2,7.0 | 2026-09-18 | 2026-09-20 | 3 | 4 | 100% | Not Started | P0 | High | Real-data results captured or explicit DSN/authority gap documented | 진행상황-개선기획.md §7
8.0 | Release readiness | Release review, rollback plan, user-facing disclosure, and go/no-go | Product / Delivery | 7.0,7.1 | 2026-09-21 | 2026-09-23 | 3 | 4 | 100% | Not Started | P0 | High | Go/no-go decision has test evidence, known limitations, and rollback owner | README operational profile; improvement plan §5
Formulas:
Finish = [Start]+2-1

## Milestones
QuantAgent Delivery Milestones
Milestone dates update from the README planning start date through linked WBS schedule formulas.
Milestone | Target Date | Owner Role | Linked WBS | Exit / Evidence | Status | Priority | Risk | Schedule Check | Notes
M0 — Planning baseline approved | 2026-08-18 | Product / Delivery | 1.0,1.1 | Scope, validation matrix, cadence, and evidence register approved | Not Started | P0 | Medium | On track
M1 — Truthful FE copy released | 2026-08-20 | Frontend Engineer | 2.0,2.1 | Unsupported walk-forward claim removed; regression test passes | Not Started | P0 | Low | On track
M2 — Point-in-time universe validated | 2026-08-27 | Data / Backend + QA | 3.0,3.1,3.2 | As-of query, automated tests, and authorized real-data ranking evidence complete | Not Started | P0 | High | On track
M3 — Holdout reporting released | 2026-09-02 | AI / Backend + Frontend | 4.0,4.1 | Holdout headline, candidate N, DSR, and contract tests complete | Not Started | P0 | High | On track
M4 — Abstention gate and UX validated | 2026-09-10 | AI / Quant + QA | 5.0,5.1,5.2 | Gate decision, reason code, no-recommendation UX, and validation evidence complete | Not Started | P0 | High | On track
M5 — Warm-up correctness locked | 2026-09-06 | AI / Quant + QA | 6.0,6.1 | Pre-window values unavailable and regression tests pass | Not Started | P1 | Medium | On track
M6 — Release go/no-go | 2026-09-23 | Product / Delivery | 7.0,7.1,8.0 | Automated suite, real-data limits, rollback, disclosure, and decision recorded | Not Started | P0 | High | Review date

## Risks
QuantAgent Delivery Risk Register
Risk score and response priority are formula-driven from editable probability and impact inputs. High-risk items require an explicit owner and review cadence.
Risk ID | Risk / Trigger | Probability | Impact | Score | Level | Owner Role | Mitigation / Contingency | Linked WBS | Review Cadence | Status
R-01 | Authorized real-data DSN is unavailable, preventing point-in-time ranking and gate validation | 60% | 5 | 3 | Low | QA / Quant Research | Use deterministic fixture checks; log validation gap; schedule authorized-environment run before go/no-go | 3.2,5.2,7.1 | Weekly | Open
R-02 | Point-in-time universe changes candidate selection or visibly lowers headline return | 80% | 5 | 4 | Low | Product + Quant Research | Pre-brief stakeholders; publish measurement rationale; compare candidates and holdout results | 3.0-3.2,4.0 | Weekly | Open
R-03 | Abstention gate produces more no-recommendation states than product expectations | 60% | 4 | 2.4 | Low | AI / Quant + Product | Define UX copy and decision policy; monitor trigger rate; never treat abstention as failure | 5.0-5.2 | Weekly | Open
R-04 | Metric/API changes drift from FE labels or consumers | 40% | 4 | 1.6 | Low | Frontend + QA | Version contract fixtures and run targeted API/FE regression suite | 4.0,4.1,7.0 | Weekly | Open
R-05 | Warm-up enforcement changes early trades and causes unexpected result deltas | 50% | 3 | 1.5 | Low | AI / Quant Engineer | Add before/after fixture baselines; document expected early-window behavior | 6.0,6.1 | Weekly | Open
R-06 | Release occurs without rollback evidence or disclosure of remaining limits | 30% | 5 | 1.5 | Low | Product / Delivery | Require release checklist, rollback owner, and known-limitations sign-off | 8.0 | At go/no-go | Open

## README
QuantAgent WBS — Read Me
A source-backed, editable execution baseline for correctness and operational-stability remediation. This workbook is a plan, not a statement that real-data validation is complete.
Planning Controls | Value | Formula / Meaning | Portfolio Summary | Value | Formula / Meaning
Planning horizon | 12 weeks | Editable planning baseline |  | Total work items | 17
Planning start date | 46251 | Editable input used by WBS start/finish formulas |  | Planned effort days | 68
Target release date |  | Formula: final planned WBS finish |  | Planned duration days | 38
Named owners | Not established | Role-based ownership is intentional until capacity is confirmed |  | Average completion | 88.24%
Source status | 2026-08-17 | See source registry below |  | Open high risks | 0
Real-data validation | 2026-09-23 | Not represented as complete without authorized execution |  | Schedule state | No high risks
Color convention | Blue = editable; Green = cross-sheet link; Black = formula | Inputs may be updated after project staffing/release alignment |  | Formula health | OK
Source registry and planning rationale
Source | Scope used | Planning implication | Key remediation | Sequence | Acceptance theme
README.md | MVP spine and deterministic/production execution contracts | Plan preserves FE → AI API → backtest dependency and verification gates | P-4 | 1 | Remove unsupported walk-forward wording
진행상황-개선기획.md | Prioritized remediation and measured rationale | P-4, P-1, P-3, P-2, P-5 are sequenced as documented | P-1 | 2 | As-of liquid universe + evidence
진행상황-문제정의-2.md | Correctness and operational risks | Warm-up and transparent out-of-sample reporting are explicit acceptance gates | P-3 | 3 | Holdout-only headline, candidate N, DSR
docs/PROJECT_FLOW_AND_DEBT_GUIDE.md | Actual system topology and debt map | Owners and release checks span FE, AI, backtest, DE, and QA interfaces | P-2 | 4 | Abstain rather than make unsupported recommendation
진행상황-개선기획.md | Start-order table | Warm-up is localized after evidence and reporting safeguards | P-5 | 5 | No pre-window indicator signal
Use this workbook
1. Set the planning start date in B9. 2. Replace role owners with named owners and update status/progress. 3. Preserve formula cells in green/black so schedule and summary remain auditable. 4. Treat DSN-gated real-data validation as an open release gate until evidence is captured.