## WBS
QuantAgent 개선 작업 분해 구조(WBS)
편집 가능한 12주 계획 기준선입니다. 시작일·역할·상태·우선순위·위험도는 계획 기본값이며, 인력 및 출시일 확정 후 파란색 입력값을 갱신하십시오.
WBS ID | 작업영역 | 작업 / 산출물 | 담당 역할 | 선행 작업 | 시작일 | 종료일 | 기간(일) | 투입(인일) | 진척률 | 상태 | 우선순위 | 위험도 | 완료 기준 | 근거 / 출처 | 비고
1.0 | 프로그램 관리 | 착수, 범위 확정, 전달 주기 및 근거 등록부 수립 | 제품 / 딜리버리 |  | 2026-08-17 | 2026-08-18 | 2 | 3 | 0% | 미착수 | P0 | 중간 | 담당 역할을 배정하고 주간 주기 및 완료 근거 등록부를 발행 | README.md; docs/PROJECT_FLOW_AND_DEBT_GUIDE.md | 계획 기준선
1.1 | 프로그램 관리 | 재현 가능한 픽스처 및 실데이터 검증 매트릭스 작성 | QA / 퀀트 리서치 | 1.0 | 2026-08-18 | 2026-08-21 | 4 | 4 | 0% | 미착수 | P0 | 높음 | 픽스처·통합·DSN 게이트 실데이터 검증을 모두 포함 | README.md 로컬 결정론 프로필; 진행상황-개선기획.md §7 | 실데이터 검증은 DSN 게이트 유지
2.0 | 정확한 표현 | 근거 없는 FE 워크포워드 문구 및 연관 카피 제거(P-4) | 프론트엔드 엔지니어 | 1.0 | 2026-08-20 | 2026-08-20 | 1 | 1 | 0% | 미착수 | P0 | 낮음 | 롤링 검증이 구현되지 않은 위치에 워크포워드 주장이 남아 있지 않음 | 진행상황-개선기획.md §5 P-4 | 신속·저위험 수정
2.1 | 정확한 표현 | 수정된 성과 문구의 FE 회귀 테스트 추가 | 프론트엔드 엔지니어 | 2.0 | 2026-08-21 | 2026-08-21 | 1 | 1 | 0% | 미착수 | P1 | 낮음 | 대상 FE 테스트가 제거된 주장의 재발을 차단 | FE scripts; 진행상황-개선기획.md §5
3.0 | 시점 정합 데이터 | 직전 90일 거래대금 기반 시점 정합 유동성 유니버스 쿼리 구현(P-1) | 데이터 / 백엔드 엔지니어 | 1.0 | 2026-08-22 | 2026-08-25 | 4 | 5 | 0% | 미착수 | P0 | 높음 | 백테스트 시작일 기준 유니버스를 계산하며 현재 시가총액 선택을 사용하지 않음 | 진행상황-개선기획.md §7 P-1; ai/ai_graph/data_sources/db.py | 인가된 환경에서만 편집 가능한 DSN 사용
3.1 | 시점 정합 데이터 | 시점 정합 유니버스 및 최소 이력 단위·통합 테스트 | QA / 데이터 엔지니어 | 3.0 | 2026-08-25 | 2026-08-27 | 3 | 4 | 0% | 미착수 | P0 | 높음 | 90일 창·30건 이상 관측치·순위 결정성을 검증 | 진행상황-개선기획.md §7 P-1
3.2 | 시점 정합 데이터 | 실데이터에서 후보 순위 변경을 재현하고 근거 확보 | 퀀트 리서치 | 3.1 | 2026-08-28 | 2026-08-31 | 4 | 5 | 0% | 미착수 | P0 | 높음 | DSN 사용 하니스가 생존편향 대비 시점 정합 후보 순위를 기록 | 진행상황-개선기획.md §7 실데이터 재현 | 인가된 DSN이 제공될 때까지 차단
4.0 | 표본외 보고 | 홀드아웃 전용 헤드라인 지표·후보 수·디플레이트 샤프 공개(P-3) | AI / 백엔드 엔지니어 | 3.1 | 2026-08-29 | 2026-09-02 | 5 | 6 | 0% | 미착수 | P0 | 높음 | 헤드라인은 미사용 홀드아웃을 사용하고 보고서에 후보 N·DSR·근거를 표시 | 진행상황-개선기획.md §2 P-3; §5 | DSR 하드 게이트 금지
4.1 | 표본외 보고 | 투명 지표용 보고서·FE 투영 및 API 계약 테스트 갱신 | 프론트엔드 + QA | 4.0 | 2026-09-02 | 2026-09-04 | 3 | 4 | 0% | 미착수 | P0 | 중간 | API·UI 계약 테스트가 지표 라벨과 값을 일치시킴 | README MVP spine; ai/tests/contracts; fe scripts
5.0 | 추천 안전성 | 3개 폴드 일관성 기반 기권 게이트 구현(P-2) | AI / 퀀트 엔지니어 | 4.0 | 2026-09-03 | 2026-09-08 | 6 | 7 | 0% | 미착수 | P0 | 높음 | 3/3 양의 폴드와 평균 샤프 0.5 이상이 아니면 추천을 보류 | 진행상황-개선기획.md §7 P-2 | 기권과 실패를 명확히 구분
5.1 | 추천 안전성 | 기권 상태·사유 코드·'추천 없음' UX 테스트 | QA + 프론트엔드 | 5.0 | 2026-09-08 | 2026-09-10 | 3 | 4 | 0% | 미착수 | P0 | 중간 | UI가 현금/추천 없음 상태와 API 사유를 명확히 표시 | 진행상황-개선기획.md §5 P-2
5.2 | 추천 안전성 | 실데이터에서 게이트 발동률 및 수익 분산 효과 측정 | 퀀트 리서치 | 5.1 | 2026-09-11 | 2026-09-13 | 3 | 4 | 0% | 미착수 | P1 | 높음 | 근거가 계획 발동률과 분산 비교 결과를 기록 | 진행상황-개선기획.md §5 P-2; §7 | DSN 게이트
6.0 | 백테스트 정확성 | 지표 워밍업/최소 기간 강제 적용(P-5) | AI / 퀀트 엔지니어 | 1.1 | 2026-09-04 | 2026-09-06 | 3 | 4 | 0% | 미착수 | P1 | 중간 | 필요 룩백 이전의 지표는 NaN 또는 사용 불가 | 진행상황-개선기획.md §2 P-5
6.1 | 백테스트 정확성 | 이력 부족 및 초기 구간 신호 회귀 테스트 추가 | QA / 퀀트 엔지니어 | 6.0 | 2026-09-07 | 2026-09-08 | 2 | 3 | 0% | 미착수 | P1 | 중간 | 관련 모든 룩백의 초기 구간 신호를 거부 또는 보류하는 테스트 | 진행상황-문제정의-2.md A-2; 진행상황-개선기획.md §5
7.0 | 출시 보증 | 대상 단위·계약·통합·픽스처 스모크 테스트 실행 | QA 엔지니어 | 2.1,4.1,5.1,6.1 | 2026-09-14 | 2026-09-17 | 4 | 5 | 0% | 미착수 | P0 | 높음 | 대상 검증이 모두 통과하고 실패는 담당자·근거와 함께 분류 | README 검증 계약; 프로젝트 테스트
7.1 | 출시 보증 | 인가된 실데이터 검증 실행 및 한계 문서화 | QA + 퀀트 리서치 | 3.2,5.2,7.0 | 2026-09-18 | 2026-09-20 | 3 | 4 | 0% | 미착수 | P0 | 높음 | 실데이터 결과 또는 명시적인 DSN/권한 공백을 문서화 | 진행상황-개선기획.md §7
8.0 | 출시 준비 | 출시 검토, 롤백 계획, 사용자 공지 및 출시 여부 결정 | 제품 / 딜리버리 | 7.0,7.1 | 2026-09-21 | 2026-09-23 | 3 | 4 | 0% | 미착수 | P0 | 높음 | 출시 여부 결정에 테스트 근거·알려진 한계·롤백 담당자를 포함 | README 운영 프로필; 개선 기획 §5
Formulas:
종료일 = [시작일]+2-1

## Milestones
QuantAgent 주요 마일스톤
마일스톤 날짜는 README의 계획 시작일과 연결된 WBS 일정 수식에 따라 갱신됩니다.
마일스톤 | 목표일 | 담당 역할 | 연결 WBS | 완료 / 근거 | 상태 | 우선순위 | 위험도 | 일정 점검 | 비고
M0 — 계획 기준선 승인 | 2026-08-18 | 제품 / 딜리버리 | 1.0,1.1 | 범위·검증 매트릭스·전달 주기·근거 등록부 승인 | 미착수 | P0 | 중간 | 정상
M1 — 정확한 FE 문구 출시 | 2026-08-20 | 프론트엔드 엔지니어 | 2.0,2.1 | 근거 없는 워크포워드 주장을 제거하고 회귀 테스트 통과 | 미착수 | P0 | 낮음 | 정상
M2 — 시점 정합 유니버스 검증 | 2026-08-27 | 데이터 / 백엔드 + QA | 3.0,3.1,3.2 | 시점 쿼리·자동 테스트·인가된 실데이터 순위 근거 완료 | 미착수 | P0 | 높음 | 정상
M3 — 홀드아웃 보고 출시 | 2026-09-02 | AI / 백엔드 + 프론트엔드 | 4.0,4.1 | 홀드아웃 헤드라인·후보 N·DSR·계약 테스트 완료 | 미착수 | P0 | 높음 | 정상
M4 — 기권 게이트 및 UX 검증 | 2026-09-10 | AI / 퀀트 + QA | 5.0,5.1,5.2 | 게이트 결정·사유 코드·추천 없음 UX·검증 근거 완료 | 미착수 | P0 | 높음 | 정상
M5 — 워밍업 정확성 고정 | 2026-09-06 | AI / 퀀트 + QA | 6.0,6.1 | 사전 구간 값 사용 불가 및 회귀 테스트 통과 | 미착수 | P1 | 중간 | 정상
M6 — 출시 여부 결정 | 2026-09-23 | 제품 / 딜리버리 | 7.0,7.1,8.0 | 자동화 스위트·실데이터 한계·롤백·공지·결정을 기록 | 미착수 | P0 | 높음 | 정상

## Risks
QuantAgent Delivery Risk Register
Risk score and response priority are formula-driven from editable probability and impact inputs. High-risk items require an explicit owner and review cadence.
Risk ID | Risk / Trigger | Probability | Impact | Score | Level | Owner Role | Mitigation / Contingency | Linked WBS | Review Cadence | Status
R-01 | Authorized real-data DSN is unavailable, preventing point-in-time ranking and gate validation | 60% | 5 | 3 | Medium | QA / Quant Research | Use deterministic fixture checks; log validation gap; schedule authorized-environment run before go/no-go | 3.2,5.2,7.1 | Weekly | Open
R-02 | Point-in-time universe changes candidate selection or visibly lowers headline return | 80% | 5 | 4 | High | Product + Quant Research | Pre-brief stakeholders; publish measurement rationale; compare candidates and holdout results | 3.0-3.2,4.0 | Weekly | Open
R-03 | Abstention gate produces more no-recommendation states than product expectations | 60% | 4 | 2.4 | Medium | AI / Quant + Product | Define UX copy and decision policy; monitor trigger rate; never treat abstention as failure | 5.0-5.2 | Weekly | Open
R-04 | Metric/API changes drift from FE labels or consumers | 40% | 4 | 1.6 | Low | Frontend + QA | Version contract fixtures and run targeted API/FE regression suite | 4.0,4.1,7.0 | Weekly | Open
R-05 | Warm-up enforcement changes early trades and causes unexpected result deltas | 50% | 3 | 1.5 | Low | AI / Quant Engineer | Add before/after fixture baselines; document expected early-window behavior | 6.0,6.1 | Weekly | Open
R-06 | Release occurs without rollback evidence or disclosure of remaining limits | 30% | 5 | 1.5 | Low | Product / Delivery | Require release checklist, rollback owner, and known-limitations sign-off | 8.0 | At go/no-go | Open

## README
QuantAgent WBS — Read Me
A source-backed, editable execution baseline for correctness and operational-stability remediation. This workbook is a plan, not a statement that real-data validation is complete.
Planning Controls | Value | Formula / Meaning | Portfolio Summary | Value | Formula / Meaning
Planning horizon | 12 weeks | Editable planning baseline |  | Total work items | 17
Planning start date | 2026-08-17 | Editable input used by WBS start/finish formulas |  | Planned effort days | 68
Target release date | 2026-09-23 | Formula: final planned WBS finish |  | Planned duration days | 38
Named owners | Not established | Role-based ownership is intentional until capacity is confirmed |  | Average completion | 0%
Source status | Repository evidence | See source registry below |  | Open high risks | 1
Real-data validation | DSN-gated | Not represented as complete without authorized execution |  | Schedule state | Review high risks
Color convention | Blue = editable; Green = cross-sheet link; Black = formula | Inputs may be updated after project staffing/release alignment |  | Formula health | OK
Source registry and planning rationale
Source | Scope used | Planning implication | Key remediation | Sequence | Acceptance theme
README.md | MVP spine and deterministic/production execution contracts | Plan preserves FE → AI API → backtest dependency and verification gates | P-4 | 1 | Remove unsupported walk-forward wording
진행상황-개선기획.md | Prioritized remediation and measured rationale | P-4, P-1, P-3, P-2, P-5 are sequenced as documented | P-1 | 2 | As-of liquid universe + evidence
진행상황-문제정의-2.md | Correctness and operational risks | Warm-up and transparent out-of-sample reporting are explicit acceptance gates | P-3 | 3 | Holdout-only headline, candidate N, DSR
docs/PROJECT_FLOW_AND_DEBT_GUIDE.md | Actual system topology and debt map | Owners and release checks span FE, AI, backtest, DE, and QA interfaces | P-2 | 4 | Abstain rather than make unsupported recommendation
진행상황-개선기획.md | Start-order table | Warm-up is localized after evidence and reporting safeguards | P-5 | 5 | No pre-window indicator signal
Use this workbook
1. Set the planning start date in B6. 2. Replace role owners with named owners and update status/progress. 3. Preserve formula cells in green/black so schedule and summary remain auditable. 4. Treat DSN-gated real-data validation as an open release gate until evidence is captured.